## Template
EXAMPLE: Customer Database Risk Assessment
Step 1: Asset Characterization Asset ID: AST-001 Asset Name: Customer Database (PostgreSQL on AWS RDS) Owner: Marcus Bellwood (CTO) Location: AWS RDS, us-west-2 region Description: Contains customer company info, user credentials (hashed), project data, usage logs Criticality: CRITICAL - Core to product, contains customer PII, service depends on it
Step 2: Threat Identification THREAT 1: Unauthorized Data Access • Threat Actors: External attackers, malicious insiders • Attack Vectors: SQL injection, compromised credentials, misconfigured access controls • Motivation: Data theft for sale, competitive intelligence, ransomware • Current Controls: Parameterized queries, AWS IAM roles, network security groups, password complexity • Vulnerabilities: No database activity monitoring, admin credentials in plaintext scripts, no MFA on DB admin accounts, irregular access reviews THREAT 2: Data Loss/Corruption • Threat Actors: System failure, ransomware, malicious insider • Attack Vectors: Hardware failure, crypto-locker malware, deliberate deletion • Current Controls: Automated daily backups to S3, database replication, 7- day retention • Vulnerabilities: Backups never tested, no offline/immutable backup, RTO/RPO not defined
Step 3: Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Database attacks extremely common in SaaS sector. Recent GitHub credential incident shows vulnerability. Limited monitoring makes detection difficult. High-value target (customer data). Some basic controls reduce from 5 to 4. THREAT 2 Likelihood: 2 (UNLIKELY) Justification: AWS RDS high availability architecture. Automated backups in place. But untested restoration is a concern
Step 4: Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: CCPA/GDPR fines ($50K-$500K), contract penalties ($100K+), incident response ($50K-$100K) Operational: Service shutdown during investigation, 10-30% customer churn Reputational: Loss of enterprise prospects permanently, negative press, difficulty winning new business 1-2 years THREAT 2 Impact: 4 (MAJOR) Financial: Revenue loss $10K-$50K/day, SLA penalties $20K-$100K, recovery costs $30K-$80K Operational: Service downtime 1-3 days estimated
Step 5: Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Unauthorized | 4 | 5 | 4 x 5 = 20 | Critical
Data Loss/Corruption | 2 | 4 | 2 x 4 = 8 | Medium
Treatment Priority: Threat 1 (Unauthorized Access) = IMMEDIATE ACTION REQUIRED. Threat 2 (Data Loss) = Address within 6 months.

## Version
Issue date | Version
2026-04-12 | v1.0
2026-04-14 | v1.1

## Definition
Risk Assessment Methodology: For each critical asset: 1. Identify threats (what could go wrong?) 2. Identify vulnerabilities (what weaknesses exist?) 3. Assess likelihood (how likely is this threat to exploit this vulnerability?) 4. Assess impact (what would be the consequence?) 5. Calculate risk level (Likelihood × Impact) 6. Document current controls 7. Determine residual risk and treatment priority
Risk Levels: 1-5 = LOW (green) ¦ 6-10 = MEDIUM (yellow) ¦ 11-15 = HIGH (orange) ¦ 16-25 = CRITICAL (red)

## DAT-001
Customer Database Risk Assessment
Asset Characterization Asset ID: DAT-001 Asset Name: Customer Database (PostgreSQL on AWS RDS) Owner: Derek Ramsey (Sales Director) Location: AWS RDS, us-west-2 region Description: Contains customer company info, user credentials (hashed), project data, usage logs Criticality: CRITICAL - Core to product, contains customer PII, service depends on it
Threat Identification THREAT 1: Unauthorized Data Access + Threat Actors: External attackers, malicious insiders + Attack Vectors: SQL injection, compromised credentials, misconfigured access controls + Motivation: Data theft for sale, competitive intelligence, ransomware + Current Controls: Parameterized queries, AWS IAM roles, network security groups, password complexity + Vulnerabilities: No database activity monitoring, admin credentials in plaintext scripts, no MFA on DB admin accounts, irregular access reviews THREAT 2: Data Loss/Corruption + Threat Actors: System failure, ransomware, malicious insider + Attack Vectors: Hardware failure, crypto-locker malware, deliberate deletion + Current Controls: Automated daily backups to S3, database replication, 7-day retention + Vulnerabilities: Backups never tested, no offline/immutable backup, RTO/RPO not defined
Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Database attacks extremely common in SaaS sector. Recent GitHub credential incident shows vulnerability. Limited monitoring makes detection difficult. High-value target (customer data). Some basic controls reduce from 5 to 4. THREAT 2 Likelihood: 2 (UNLIKELY) Justification: AWS RDS high availability architecture. Automated backups in place. But untested restoration is a concern
Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: CCPA/GDPR fines ($50K-$500K), contract penalties ($100K+), incident response ($50K-$100K) Operational: Service shutdown during investigation, 10-30% customer churn Reputational: Loss of enterprise prospects permanently, negative press, difficulty winning new business 1-2 years THREAT 2 Impact: 4 (MAJOR) Financial: Revenue loss $10K-$50K/day, SLA penalties $20K-$100K, recovery costs $30K-$80K Operational: Service downtime 1-3 days estimated
Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Unauthorized | 4 | 5 | 4 x 5 = 20 | Critical
Data Loss/Corruption | 2 | 4 | 2 x 4 = 8 | Medium
Treatment Priority: Threat 1 (Unauthorized Access) = IMMEDIATE ACTION REQUIRED. Threat 2 (Data Loss) = Address within 6 months.

## DAT-002
CloudFlow Source Code Risk Assessment
Asset Characterization Asset ID: DAT-002 Asset Name: CloudFlow Source Code (GitHub Repository) Owner: Nina Castellano (VP Engineering) Location: GitHub (cloud-based repository), integrated with CI/CD pipeline Description: Contains application source code, configuration files, and deployment scripts for CloudFlow platform Criticality: CRITICAL – Core intellectual property; compromise may lead to system exploitation and business impact
Threat Identification THREAT 1: Source Code Leakage / Unauthorized Access + Threat Actors: External attackers, malicious insiders, compromised developer accounts + Attack Vectors: Phishing, credential theft, exposed API tokens, misconfigured repository access + Motivation: Intellectual property theft, vulnerability discovery, competitive advantage + Current Controls: Role-based access control (RBAC), private repositories, code review process, access via corporate accounts + Vulnerabilities: No MFA enforcement for all developers, lack of access review, secrets potentially stored in code, insufficient monitoring of repository access THREAT 2: Code Tampering / Malicious Injection + Threat Actors: Malicious insiders, compromised developer accounts, supply chain attackers + Attack Vectors: Unauthorized commits, compromised CI/CD pipeline, dependency injection attacks + Current Controls: Pull request workflow, code reviews, CI/CD pipeline checks + Vulnerabilities: No mandatory code signing, insufficient branch protection rules, lack of automated security scanning (SAST/DAST), weak CI/CD access control
Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Source code repositories are common targets in SaaS environments. Developers may reuse passwords or fall victim to phishing. Lack of enforced MFA increases exposure. High-value intellectual property increases attacker motivation. THREAT 2 Likelihood: 3 (POSSIBLE) Justification: Code tampering requires elevated access but is feasible via compromised accounts or insider threats. Existing code review reduces likelihood but gaps in pipeline security remain.
Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: Loss of competitive advantage, potential revenue loss $100K–$500K+, incident response costs Operational: Increased risk of exploitation of vulnerabilities, emergency patching required Reputational: Loss of customer trust, reduced confidence from enterprise clients THREAT 2 Impact: 5 (CRITICAL) Financial: Cost of incident response, remediation, and potential SLA penalties Operational: Deployment of compromised code, system compromise, service disruption Reputational: Severe trust impact if customers affected by malicious code
Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Source Code Leakage | 4 | 5 | 4 x 5 = 20 | Critical
Code Tampering | 3 | 5 | 3 x 5 = 15 | High
Threat 1 (Source Code Leakage): IMMEDIATE ACTION REQUIRED Threat 2 (Code Tampering): HIGH PRIORITY – Address within 3–6 months

## SER-001
AWS Infrastructure Risk Assessment
Asset Characterization Asset ID: SER-001 Asset Name: AWS Infrastructure (EC2, S3, RDS, VPC) Owner: Nina Castellano (VP Engineering) Location: AWS Cloud (us-west-2 region) Description: Provides core cloud infrastructure for CloudFlow, including compute, storage, networking, and database services Criticality: CRITICAL – Backbone of all services; compromise impacts availability, security, and operations
Threat Identification THREAT 1: Cloud Misconfiguration (Unauthorized Exposure) + Threat Actors: External attackers, internal misconfiguration by DevOps/Engineers + Attack Vectors: Public S3 buckets, overly permissive IAM roles, open security groups, exposed ports + Motivation: Data theft, exploitation, reconnaissance + Current Controls: IAM roles and policies, security groups, basic network segmentation, AWS default security settings + Vulnerabilities: No continuous configuration monitoring, lack of automated compliance checks, excessive privileges in IAM roles, no centralized logging (CloudTrail not fully enabled), lack of periodic review THREAT 2: Service Disruption / Denial of Service + Threat Actors: External attackers (DDoS), system failures, cloud service outages + Attack Vectors: Traffic flooding, resource exhaustion, dependency failure (AWS outage) + Current Controls: AWS availability zones, auto-scaling, basic monitoring + Vulnerabilities: No DDoS protection (e.g., AWS Shield Advanced), no defined incident response for outages , insufficient redundancy testing, unclear failover procedures.
Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Cloud misconfiguration is one of the most common causes of data breaches in SaaS. Rapid deployment and lack of automated checks increase likelihood. Shared responsibility model requires internal control, which is currently limited. THREAT 2 Likelihood: 3 (POSSIBLE) Justification: AWS provides strong infrastructure resilience, reducing likelihood. However, absence of advanced DDoS protection and limited failover planning introduces risk.
Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: Data breach costs, regulatory fines (GDPR/CCPA), contract penalties $100K+ Operational: Unauthorized access to systems, potential system compromise Reputational: Loss of customer trust, impact on enterprise contracts THREAT 2 Impact: 5 (CRITICAL) Financial: Revenue loss $10K–$50K/day, SLA penalties, recovery costs Operational: Service downtime across CloudFlow platform Reputational: Customer dissatisfaction, loss of trust and churn
Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Cloud Misconfiguration | 4 | 5 | 4 x 5 = 20 | Critical
Service Disruption / DoS | 3 | 5 | 3 x 5 = 15 | High
Threat 1 (Cloud Misconfiguration): IMMEDIATE ACTION REQUIRED Threat 2 (Service Disruption): HIGH PRIORITY – Address within 3–6 months

## SER-002
Auth0 Risk Assessment
Asset Characterization Asset ID: SER-002 Asset Name: Authentication Service (Auth0) Owner: Nina Castellano (VP Engineering) Location: Auth0 Cloud Service (Third-party SaaS) Description: Provides authentication and authorization services for CloudFlow users, including login, token management, and identity federation Criticality: CRITICAL – Controls access to all systems; compromise may lead to full account takeover and data exposure
Threat Identification THREAT 1: Account Takeover / Authentication Bypass + Threat Actors: External attackers, credential stuffing bots, malicious users + Attack Vectors: Phishing, credential reuse, brute force attacks, token theft, weak authentication configurations + Motivation: Unauthorized access to customer accounts, data theft, privilege escalation + Current Controls: Password policies, basic authentication mechanisms, token-based authentication (JWT), login rate limiting + Vulnerabilities: No enforced MFA for all users, lack of anomaly detection, weak password reuse control, insufficient monitoring of login activities THREAT 2: Misconfiguration of Authentication / Authorization Rules + Threat Actors: Internal misconfiguration, developers, compromised admin accounts + Attack Vectors: Incorrect role/permission assignment, flawed access rules, insecure token configuration + Current Controls: Role-based access control (RBAC), predefined authentication flows + Vulnerabilities: Lack of periodic access review, no strict least privilege enforcement, insufficient validation of role assignments, no automated configuration checks
Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Credential-based attacks (phishing, credential stuffing) are highly prevalent in SaaS platforms. Absence of enforced MFA significantly increases likelihood. Authentication systems are a primary attack target. THREAT 2 Likelihood: 3 (POSSIBLE) Justification: Misconfiguration risks exist due to complexity of authentication rules. RBAC provides some control, but lack of review and automation increases risk.
Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: Data breach costs, contract penalties, incident response costs $50K–$200K Operational: Unauthorized access to multiple accounts, potential system-wide compromise Reputational: Loss of customer trust, severe impact on enterprise clients THREAT 2 Impact: 4 (MAJOR) Financial: Potential unauthorized access leading to data exposure, remediation costs Operational: Privilege escalation, unauthorized actions within system Reputational: Moderate to high impact depending on scope of misconfiguration
Step 5: Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Account Takeover | 4 | 5 | 4 x 5 = 20 | Critical
Misconfiguration of Auth Rules | 3 | 4 | 3 x 4 = 12 | High
Threat 1 (Account Takeover): IMMEDIATE ACTION REQUIRED Threat 2 (Misconfiguration): HIGH PRIORITY – Address within 3–6 months

## SOF-001
CloudFlow Source Application Risk Assessment
Asset Characterization Asset ID: SOF-001 Asset Name: CloudFlow Application (Web & API) Owner: Nina Castellano (VP Engineering) Location: Hosted on AWS (EC2 / containerized services), accessed via web and mobile clients Description: Core SaaS application providing project management functionalities, including task management, collaboration, file sharing, and reporting Criticality: CRITICAL – Primary customer-facing system; directly impacts service availability and data security
Threat Identification THREAT 1: Web Application Attacks (OWASP Top 10) + Threat Actors: External attackers, automated bots + Attack Vectors: SQL injection, XSS, CSRF, insecure APIs, broken access control + Motivation: Data theft, unauthorized access, system exploitation + Current Controls: Input validation, authentication mechanisms, basic access control, HTTPS encryption + Vulnerabilities: Lack of regular penetration testing, no automated vulnerability scanning (SAST/DAST), insufficient API security controls, inconsistent input validation across modules THREAT 2: Application Downtime / Service Failure + Threat Actors: System failures, deployment errors, infrastructure dependency issues + Attack Vectors: Faulty deployment, software bugs, resource exhaustion + Current Controls: CI/CD pipeline, basic monitoring, cloud infrastructure redundancy + Vulnerabilities: No defined rollback procedures, limited monitoring coverage, no formal incident response playbook, insufficient load testing
Likelihood Assessment THREAT 1 Likelihood: 4 (LIKELY) Justification: Web applications are primary targets for attackers. OWASP vulnerabilities are common in SaaS platforms. Lack of regular security testing increases likelihood. THREAT 2 Likelihood: 3 (POSSIBLE) Justification: Modern deployment pipelines reduce risk, but absence of rollback and testing increases probability of service disruption.
Impact Assessment THREAT 1 Impact: 5 (CRITICAL) Financial: Data breach costs, regulatory fines, contract penalties $100K+ Operational: Unauthorized access, system compromise Reputational: Severe loss of customer trust, impact on enterprise clients THREAT 2 Impact: 5 (CRITICAL) Financial: Revenue loss $10K–$50K/day, SLA penalties Operational: Service outage affecting all users Reputational: Customer dissatisfaction, churn
Risk Calculation Threat Likelihood Impact Risk Score Risk Level
Threat | Likelihood | Impact | Risk Score | Risk Level
Web Application Attacks | 4 | 5 | 4 x 5 = 20 | Critical
Application Downtime | 3 | 5 | 3 x 5 = 15 | High
Threat 1 (Web Application Attacks): IMMEDIATE ACTION REQUIRED Threat 2 (Application Downtime): HIGH PRIORITY – Address within 3–6 months